## Sheet1
# | Item | Category | Description of required changes | Big ticket? | Status | Assigned to
1 | Develop and approve project timeline | Project management |  |  | Completed
2 | Create draft D0.1 from 1904.1-2017 package A. | Project management |  | YES | Completed
3 | ULID provisioning | LLID provisioning |  | YES | Completed | Glen Kramer
4 | GLID provisioning | LLID provisioning |  | YES | Assigned | Glen Kramer
5 | Multicast ULID provisioning | LLID provisioning |  | YES | Completed | Glen Kramer
6 | Report format and queue length calculation | Granting/Reporting | New behavior: gratuitous reports, dynamic reporting priorities | YES | Assigned | Glen Kramer
7 | Multicast operation | New 802.3ca behavior | Based on multicast ULID | YES | Assigned | Glen Kramer
8 | Transceiver status monitoring | New 802.3ca behavior | Similar, but should be wavelength-specific | NO | Unassigned
9 | Port selective loopback | New 802.3ca behavior | Maybe different to enable inter-channel loopback | NO | Unassigned
10 | Optical link protection | New 802.3ca behavior | New behavior in multi-channel PON. See slide 22 in tf4_2102_kramer_1.pdf | YES | Unassigned
11 | Data encryption | New 802.3ca behavior | 1) Zero-overhead encryption as in SIEPON, pkg.A, but envelope-based instead of frame-based. 2) Add support for 256-bit keys. 3) Specify encryption using one key per ONU, not per LLID | YES | Unassigned
12 | Power saving | New 802.3ca behavior | Consider additional multi-channel mode | YES | Assigned | Marek Hajduczenia
13 | Device and capability discovery | New 802.3ca behavior | New capabilities (fragmentation, multiple channels, etc.) |  | Unassigned
14 | Low latency x-haul (AKA cooperative transport interface, mobile/PON coordination, Cooperative DBA) | New feature |  | YES | Assigned | Curtis Knittle
15 | LLID and mLLID object types | Management attributes | ONUs are unaware if LLID is unicast or multicast. Combine LLID and mLLID into one ObjectType. See tf4_2102_kramer_1.pdf |  | Completed | Glen Kramer
16 | aLlidReportThresholds | Management attributes | Attribute is not applicable to 25G or 50G-EPON. Remove the attribute. See tf4_2102_kramer_1.pdf. |  | Completed
17 | aOnuId | Management attributes | Per 802.3ca, the ONU has only one MAC address. |  | Completed | Glen Kramer
18 | aOnuLlidCount | Management attributes | LLID is not equivalent to L-ONU anymore. |  | Assigned | JC Marion
19 | aOnuPonPortCount | Management attributes | Need to clarify if these are physical or logical PON ports |  | Assigned | Glen Kramer
20 | aLlidForwardState | Management attributes | LLIDs don’t combine user traffic, MPCP, and OAM anymore. |  | Assigned | JC Marion
21 | aLlidOamFrameRate | Management attributes | OAM rate is per ONU now. |  | Assigned | JC Marion
22 | aOnuUniPortType | Management attributes | This attribute a superset of aOnuUniPortCount (0x00-09). Do we keep both? |  | Completed | Glen Kramer
23 | aLineRateMode | Management attributes | Need to add new downstream and upstream rates. |  | Assigned | Ryan Tucker
24 | aOnuMulticastLlid | Management attributes | ONU doesn’t know whether LLID is multicast or unicast. Just needs to report all provisioned LLID values as (Value, Type, Directionality) |  | Completed | Glen Kramer
25 | aOnuPortConfig | Management attributes | Currently, aONUPortCount tells ONU how many UNI ports to enable and how many LLIDs to register. In 802.3ca, LLIDs are directly provisioned by NMS, so no LLID count is needed. The setting and querying of UNI port count can also be done using basic attribute aPhyAdminState (0x07/0x00-25) and basic action acPhyAdminControl (0x09/0x00-05). Do we keep both methods? Should be resolved together with #3 ULID Provisioning |  | Completed | Glen Kramer
26 | aQueueConfig | Management attributes | Queues need to be associated with either LLID or UNI. Need to describe what happens to queues when the LLID is deallocated or UNI is disabled. |  | Completed | Glen Kramer
27 | Counter of jumbo frames | Management attributes | New attribute(s) are needed |  | Assigned | Steve Burroughs
28 | Counters related to fragments | Management attributes | What to count and how? Proposal is needed |  | Assigned | Steve Burroughs
29 | Counters related to envelopes | Management attributes | New atrtibute(s) are needed |  | Assigned | Steve Burroughs
30 | Counters related to separate channels in 50G-EPON | Management attributes | Discuss if we just need new attributes or also object types to use channels or context objects for various attributes |  | Assigned | Steve Burroughs
31 | Redefine alarm thresholds | Management attributes | Instead of “high” and “low” thresholds, use “set” and “clear” thresholds and allow the “set” threshold be greater or less than the “clear” threshold. See tf4_2102_kramer_1.pdf |  | Assigned | Steve Burroughs
32 | aFecMode | Management attributes | Change is needed to indicate new data rates. Default should be set to enabled. Also, FEC should be per ONU, not per LLID. |  | Assigned | Marek Hajduczenia
33 | aOnuPwrSavingCap | Management attributes | Change may be needed to add new power saving modes in a multi-channel 50G-EPON. Should be resolved togetrher with #12 Power Saving |  | Assigned | Marek Hajduczenia
34 | aEeeStatus | Management attributes | What happens when aEeeStatus is set to enabled, but the UNI does not support the EEE function? Need to support querying the ONU capability separately in addition to enabling/disabling the feature. |  | Assigned | Marek Hajduczenia
35 | aPoeStatus | Management attributes | What happens when aPoeStatus is set to enabled, but the UNI does not support the PoE function? Need to support querying the ONU capability separately in addition to enabling/disabling the feature. |  | Assigned | Marek Hajduczenia
36 | aMediaType | Management attributes | Not clear what specific difference this attribute makes at the ONU. Can it be set in conflict with aPhyType (0x07/0x00-20)? The attribute purpose and function need to be clarified. |  | Assigned | Marek Hajduczenia
37 | Allocate new branch codes different from 1904.1 package A. | Management attributes |  |  | Completed | Glen Kramer
38 | Alternative term to replace "SIEPON" | Editorial | Current TF draft uses "SIEPON" in many places. To avoid confusion we should agree on a new term to distinguish the 25G/50G version of SIEPON from the original SIEPON |  | Completed | Glen Kramer
39 | Support for TR-200 for 25G-EPON needs to be confirmed | Alignment |  |  | Assigned | Kevin Noll
40 | Review and update all relevant references in Clause 2 |  |  |  | Assigned | Marek Hajduczenia
41 | Revise OLT_CI Interface definition |  |  |  | Assigned | Glen Kramer
42 | align the architecture described in Clause 5 with that of 802.3ca | New 802.3ca behavior |  |  | Assigned | Glen Kramer
43 | Attribute to discover whether ONU supports earlier versions of EPON
44 | Attribute to discover optical module version |  |  |  | Assigned | Marek Hajduczenia
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101